Synthesis Project Skill Tracking and Progress

Skills looking to Claim (currently have 13 but definitely some more that I have missed)

Feasibility Study (S)

Ethics for Engineering (S)

Change Management (S)

Quality Management System (S)

Scientific Communication (S)

Market Analysis (S)

Product Production Costing (S)

Efficient Referencing (S)

Standards and Regulation (S)

Sustainable Material Management (S)

Sustainable Energy Management (S)

PCB Design for Manufacturing (S)

Signal Integrity (S)

Thermal Design (S)

Software Development and Testing (S)

Engineering Design for a Circular Economy (S)

Regenerative Design (S)

Machine Learning (S)

Risk Mitigation (S)

Being Security Minded (S)

Team Leadership (S)

Executive Summary (S)

Circuit Simulation (S)

Python Programming (S)

Hardware Description Language

Advanced Time Management (S)

Advanced Project Management (S)

Engineering Design for a Circular Economy (S)

Tracking of Skills

| Skill | Start Date | Assignee | Notes on Progress | Finish Date | Issues to Address | Written up |
| --- | --- | --- | --- | --- | --- | --- |
| Feasibility Study (S) |  | Barney/Elissa/Shyam/Joe |  |  |  |  |
| Ethics for Engineering (S) |  | Elissa |  |  |  |  |
| Change Management (S) |  | Individual |  |  |  |  |
| Scientific Communication (S) |  | Individual (but do together) |  |  | Emailed, waiting for response |  |
| Product Production Costing (S) |  | Elissa |  |  | Waiting on a unit cost |  |
| Efficient Referencing (S) |  | Elissa |  |  |  |  |
| Standards and Regulation (S) |  | Barney | - Will need to change individually - This is the standard BS EN IEC 62368-1:2024. | 21/04/2026 |  |  |
| Sustainable Material Management (S) |  | Joe |  |  | Re-write in your own words, | Write up |
| PCB Design for Manufacturing (S) |  | Elissa |  |  | Joe and Shyam meet, make changes to PCB Design (given by Elissa) + Thermal analysis |  |
| Sustainable Energy Management (S) | 28/04 | Barney | - Working on LCA | 28/04 | Completed, just needs a read through/references added to LCA diagram |  |
| Circuit Simulation (S) | 4/4/2026 | Barney | - Researched potential ways (4/4) - Started with just ON/OFF (5/4) - Incorporated V_thres as well as 555 timer (6/4) - Adjust values and finish sim (7/4) | 7/4/2026 | Barney + Shyam can use my design. Or can re-make if you want |  |
| Market Analysis (S) | 8/4/2026 | Elissa |  | 8/4/2026 |  |  |
| QMS (S) | 10/04 | Barney | - Initial structure set up, with naming document - Updated naming file format - Updated QMS fully | 29/04 |  |  |
| Python Programming (S) |  | Joe |  |  | Shyam use Joe’s Python | Write up |
| HDL (S) |  | Joe |  |  | I have included the code and screenshots (without usernames) in the teams, alter the code so its unique to you. | Write up |
| Signal Integrity (S) |  | Elissa |  |  | Joe Shyam meet, make changes (given by Elissa) |  |
| Software D&T (S) | 16/4/2026 | Shyam | - Created a UML and flowchart - Made verification tables | 18/4/2026 |  |  |
| Risk Mitigation (S) | 30/04/2026 | Shyam | - Made the matrix and written up - In engineering section | 01/05/2026 |  |  |
| Being Security Minded (S) |  | Elissa |  |  |  |  |
| Executive Summary (S) |  | Waiting (bw950) |  |  | Waiting to hear back from Fang about ‘Results’ |  |
| Team Leadership (S) | 27/4/2026 | Shyam | - Completed and written up - We need to change it for each person - Can however all use the same team charter, organisational chart and skills matrix | 27/04/2026 |  |  |
| Engineering Design for a Circular Economy (S) | 29/4/2026 | Shyam | - Document currently completed - Need to confirm calculations - Will add once checked |  |  |  |
| Thermal Design |  | Elissa |  |  | Joe + Shyam make upload changed PCB design into Ansys |  |

Advanced Time Management

Advanced Project Management (Shyam) - started 28th April, finished 29th April. Document made and is in the engineering folder in the QMS.

Regenerative Design (S)

Machine Learning (S) (Joe)

Made relevant changes to this document to add it to the github repo